## Feuil1
Proposed ACTIONS for HRS4R
Action 1 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Definition of requirements Increase funding applications and raise the employment ceiling | (+/-) 12. Recruitment (++) 26. Funding and salaries | 2024-2027, each year in autumn n for n+1.
| Responsible Unit | Indicator(s) / Target(s)
| Presidency and HR for researcher/SPE | Forecast 1397.48 FTE ; 1404.75 FTEs consumed
Action 2 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Definition of jobs description Formalise the process from the identification of needs to the drafting of job descriptions and the composition of selection committees to ensure collegiality (in connection with the cross-cutting action on the role of the Discipline Advisory Committee) | (+/-) 12. Recruitment (+/-) 15. Transparency (Code) | september 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency and HR for Researcher/SPE | Establishment of a procedure and number of distributions.
Action 3 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Assesment of applications Publicize the university's OTM-R policy | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (+/-) 15. Transparency (Code) | January 2025
| Responsible Unit | Indicator(s) / Target(s)
| HR for Researcher/SPE | Changes to the website
Action 4 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Information for candidates Once the website has been redesigned, add a link to the relevant documentation in the signatures of human resources staff. 4.1 Put a link on the Internet and Intranet sites to the National Code of Ethics for Research Professions. 4.2 Develop FAQ for selection committee’s chairmen. | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (+/-) 15. Transparency (Code) | 4.1 January 2025 and 4.2 january 2026
| Responsible Unit | Indicator(s) / Target(s)
| HRR/SPE | Modification of signatures Modification of Internet and Intranet sites. Publication of the FAQ on the Intranet and distribution to the Training & Research Units.
Action 5 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Supporting staff Continue and develop the mentoring programme. 5.1 Improve the distribution of information on mentoring. 5.2 Transform mentoring to make it accessible throughout a career (not just for new recruits). | (-/+) 21. Postdoctoral appointments (Code) (-/+) 28. Career development (-/+) 30. Access to career advice (-/+) 38. Continuing Professional Development | 5. September 2025 and September 2026. 5.1 et 5.2 June 2025
| Responsible Unit | Indicator(s) / Target(s)
| Career support department | Number of mentors and mentees. Number of communications carried out and monitoring of changes in participants' scores (attendance). Implementation of the new system.
Action 6 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Promotion to a higher grade Improve the way in which the diversity of responsibilities is taken into account and, as far as possible, take into account the reason for non-advancement given in the CNU's opinion. | (+/-) 15. Transparency (Code) (++) 16. Judging merit (Code) (+/-) 17. Variations in the chronological order of CVs (Code) | January 2026
| Responsible Unit | Indicator(s) / Target(s)
| HRR/SPE | Modification of the management guidelines for the promotion of academic staff.
Action 7 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
LECTURERS AND UNIVERSITY PROFESSORS : Promotion to a higher grade Ensure that the quota set by the Ministry is reached. | (+/-) 15. Transparency (Code) (++) 16. Judging merit (Code) (+/-) 17. Variations in the chronological order of CVs (Code) (+/-) 19. Recognition of qualifications (Code) (+/-) 20. Seniority (Code) (+/-) 22. Recognition of the profession (+/-) 25. Stability and permanence of employment (-/+) 28. Career development | January 2026
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | The quotas are set in relation to those of the Ministry.
Action 8 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
CONTRACT STAFF TEMPORARY TEACHING AND RESEARCH ASSISTANTS AND ASSOCIATES : Recruitement and transparency Improving recruitment. 8.1 Formulate and distribute job profiles containing key words on expectations. 8.2 Upgrade the SOLEIL application to develop a system for automatically replying to the next applicant, and for requesting documents as the list of successful applicants is withdrawn. 8.3 On the SOLEIL application, creation of a "type" of application tab: "associates". CONTRACT STAFF TEMPORARY TEACHING AND RESEARCH ASSISTANTS AND ASSOCIATES : Assessment of applications 8.4 Indicate the details of the votes cast in the minutes on the candidate ranking list. 8.5 Ensure that reports are filed effectively. | (+/-) 12. Recruitment (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (+/-) 15. Transparency (Code) (++) 16. Judging merit (Code) (+/-) 19. Recognition of qualifications (Code) | 8.1 and 8.2 : June 2026 8.3 : september 2027 8.4 and 8.5 June 2025
| Responsible Unit | Indicator(s) / Target(s)
| HRR/SPE International department | Number of job profiles with keywords and formalisation of the request with the international department (8.1) Formalisation of the request with the International relations department. (8.3) Contents of the minute (8.4) Number of application report (8.5)
Action 9 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
DOCTORAL AND POST-DOCTORAL CONTRACTS : recruitment and transparency Initiate discussions with the research units on post-doctoral and research contracts to facilitate recruitment in the European area for research staff at the start of their careers. 9.1 Suggest to doctoral schools that they put in place a good practice guide or guidelines in line with the OTM-R policy. DOCTORAL AND POST-DOCTORAL CONTRACTS : working conditions and environment 9.2 Repeat the surveys on the difficulties faced by doctoral students. 9.3 Generalise the provision of open workstations with IT equipment for doctoral students. | (+/-) 12. Recruitment (+/-) 13. Recruitment (Code) (++) 16. Judging merit (Code) (+/-) 19. Recognition of qualifications (Code) (-/+) 21. Postdoctoral appointments (Code) (-/+) 23. Research environment (-/+) 24. Working conditions (+/-) 25. Stability and permanence of employment (-/+) 30. Access to career advice | 9. June 2027 9.1 January 2027 9.2 June 2026 9.3 September 2027 - september 2030, september 2032
| Responsible Unit | Indicator(s) / Target(s)
| Presidency and SPE department College of doctoral schools Common documentations department | 9. Agenda meetings 9.1 Agenda meetings 9.2 Number of reports to the College of Doctoral Schools 9.3 Inventory of existing facilities. Information campaign. Partial renovation of equipment.New building facilities at the Common documentation service (CRCN West Wing). Programming phase and start of works. Partial handover of space and equipment at the SCD (CRCN West Wing).
Action 10 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
DISABILITY DOCTORAL CONTRACTS : Strengthen the institution's policy for managing and awarding disability doctoral contracts. 10.1 Consider whether or not to republish unfilled disability doctoral contracts from one year to the next (pooling or freezing and carrying over to the following year). To this end, a proposal could be made to work with Mission handicap to identify the pool of students likely to be encouraged to apply. 10.2 Consider the possibility of adjusting the number of contracts to potential applicants from year to year. | (+/-) 12. Recruitment (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (+/-) 15. Transparency (Code) | 10.1 January 2026 September 2026 2025 and every year 10.2 June 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | 10.1 Agenda meetings, numbers of masters courses and doctoral schools distributed Number of doctoral contracts with disabilities
Action 11 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
ALL ACADEMIC STAFF : operation of the disciplinary advisory committees Reconsider the role of the Disciplinary Advisory Committees (particularly with regard to the definition of job descriptions and the assessment of promotion to a higher grade). | (+/-) 12. Recruitment (+/-) 35. Participation in decision-making bodies (-/+) 38. Continuing Professional Development | January 2025
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Setting up a working group
Action 12 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS - LECTURERS RECRUITMENT Formalise cross-disciplinary information and discussion sessions and set up workshops on practices between the chairs and members of the selection committees, with the presence of the Teaching Staff Department and even the doctoral school. 12.1 Ensure that the names of the chair of the jury are mentioned on the school's website and are accessible to candidates on their Galaxie website | (+/-) 12. Recruitment (+/-) 15. Transparency (Code) | 2026 or 2027 national campaign 12.1 June 2025
| Responsible Unit | Indicator(s) / Target(s)
| HRR/SPE | Agenda meetings 12.1 List of presidents of the selection Committee with a link to the directory.
Action 13 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : ALL ACADEMIC STAFF TRAINING Strengthen training on teaching methods adapted to different statuses. 13.1 Take stock of training courses on pedagogy and improve their accessibility for different statuses. 13.2 Build up a reinforced training offer for the first few days of arrival in the university and more specific training courses, while offering the possibility of repeating this training later in the form of workshops on teaching practices. 13.3 Identify the training needs of temporary teaching and research assistants, particularly with regard to teaching. 13.4 Creation or outside intervention for first-listening training. | (-/+) 38. Continuing Professional Development (-/+) 39. Access to research training and continuous development | 13 January 2028 13.1 January 2027 13.2 January 2028 13.3 January 2027 13.4 September 2026
| Responsible Unit | Indicator(s) / Target(s)
| Career support department Doctoral schools Equality and non discrimination mission | 13 Training catalogue 13.1 Publication of the inventory 13.2 Collection of content to be passed on to the training department. 13.3 Agenda meetings. 13.4 Number of training courses per year.
Action 14 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : ALL ACADEMIC RIGHT TO DISCONNECT Creation of a guide to the rules of good digital communications, combined with recurring reminders and awareness-raising for academic staff. 14.1 Translate the "right to disconnect" into an official document. | (-/+) 23. Research environment (-/+) 24. Working conditions | 14. September 2026 14.1 September 2028
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | 14. Number of communication meetings. 14.1 Official document submitted to the university's councils, council's decisions and number of reminders.
Action 15 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : MANAGING STUDENT DISCOMFORT Provide information tools to help academic staff to guide students in difficulty. Consider the creation of discussion forums on the subject | (-/+) 24. Working conditions | January 2026
| Responsible Unit | Indicator(s) / Target(s)
| Support and integration department "API" | Communication plan
Action 16 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : WORKING CONDITIONS 16. Implementing a prevention system of psychosocial risks and developing the Social Watch system. 16.1 Carrying out a pre-diagnosis, based on available and easy-to-use indicators, to get an overview of psychosocial risks in the establishment. 16.2 Continuing to offer training on psychosocial risks and stepping up communication. 16.3 Strengthen reporting systems for psychosocial risks 16.4 Review the channels for disseminating information to raise awareness of the functions of the Social Action Department and the Social Worker. | (-/+) 23. Research environment (-/+) 24. Working conditions | 16. and 16.3 September 2025 16.1 and 16.2 June 2025
| Responsible Unit | Indicator(s) / Target(s)
| HRD and social action department | 16. Putting the new systems into operation 16.1 Summary 16.2 Number of training courses offered. Participation rates. 16.3 New social monitoring configuration. Number of communications on the system. Number of prevention actions carried out. 16.4 Number of mission presentation meetings. Number of visits to the Intranet page. Number of appointments requested following these interventions
Action 17 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : WORKING CONDITIONS Generalise the drawing up and annual updating of Single risk assessment document. Mobilise all the university's departments and faculties 17.1 Publish and make accessible information relating to the Single risk assessment document. 17.2 Develop the digital application for managing Single risk assessment documents and deploy it in addition to the existing Excel format. | (-/+) 23. Research environment (-/+) 24. Working conditions | January 2026 17.1 2025 and every year
| Responsible Unit | Indicator(s) / Target(s)
| Prevention advisor | 17 Increase in the percentage of Single risk assessment documents produced within the establishment and Updating existing Single risk assessment documents every year 17.1 Number of Single risk assessment documents published. Number of information campaigns. 17.2 New digital application.
Action 18 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : WORKING CONDITIONS Strengthen the network of prevention assistants and trained workplace first aiders in each work unit. | (-/+) 23. Research environment (-/+) 24. Working conditions | 2025 and every year
| Responsible Unit | Indicator(s) / Target(s)
| Prevention advisor | Number of meetings. Number of volunteers trained.
Action 19 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : WORKING CONDITIONS Deploy the network of mental health referrees. | (-/+) 23. Research environment (-/+) 24. Working conditions | January 2027
| Responsible Unit | Indicator(s) / Target(s)
| Prevention advisor | Mapping of mental health referrees.
Action 20 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : WORKING CONDITIONS Improving information on job changes and keeping structure sheets up to date. | (-/+) 23. Research environment (-/+) 24. Working conditions | January 2025
| Responsible Unit | Indicator(s) / Target(s)
| HRD | Information from each department on the forms.
Action 21 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : PHD SUPERVISION Gather needs, identify training opportunities and draw up a compendium of good practice for thesis supervisors. | (-/+) 23. Research environment (+/-) 36. Relation with supervisors (+/-) 37. Supervision and managerial duties (+/-) 40. Supervision | September 2026 January 2028
| Responsible Unit | Indicator(s) / Target(s)
| College of doctoral schools | Training courses Publication of the data collection
Action 22 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : PHD SUPERVISION To present to the research Committee a summary of the Individual monitoring committee reports by doctoral school on the working conditions of doctoral contracts and to define the procedures for changing thesis supervisor for serious incidents without the agreement of the thesis supervisor (opinion of the College of Doctoral Schools and decision of the President) 22.1 Designing a mediation and supervision change procedure. | (-/+) 23. Research environment (+/-) 36. Relation with supervisors (+/-) 37. Supervision and managerial duties (+/-) 40. Supervision | January 2027 22.1 : for voting in 2026
| Responsible Unit | Indicator(s) / Target(s)
| College of doctoral schools Legal and institutional affairs department | Publication of the result 22.1 Presentation of the mediation and change of supervisor procedure to the university bodies.
Action 23 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
PREVENTING PSYCHOSOCIAL RISKS : ADMINISTRATIVE DUTIES AND RESPONSIBILITIES Drawing up a sheet setting out the objectives of the assignment, the responsibilities associated with the administrative functions and the administrative contacts. | (-/+) 23. Research environment (+/-) 33. Teaching (+/-) 37. Supervision and managerial duties | January 2028
| Responsible Unit | Indicator(s) / Target(s)
| Working group | Setting up a working group
Action 24 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : EQUALITY AND NON-DISCRIMINATION Develop a range of training courses on non-discrimination, either in-house or via external partners, organised around milestones over several years, with incentives for new arrivals and those in positions of responsibility. 24.1 Develop video clips on non-discrimination. 24.2 Design and transmission of resources on selection bias prior to the Equality and Non-Discrimination Mission's involvement with Selection committee’s chairmen | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (+/-) 17. Variations in the chronological order of CVs (Code) (+/-) 27. Gender balance | 24. 2024-2027 24.1 June 2027 24.2 June 2028
| Responsible Unit | Indicator(s) / Target(s)
| Equality and non discrimination mission | Number of training courses in the catalogue. Number of training courses carried out per year in the departments concerned. Number of departments involved. Percentage of staff trained per department. 24.1 Number of capsules made available 24.2 : Number of views
Action 25 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : EQUALITY AND NON-DISCRIMINATION Draw up statistical tables documenting the number of applications selected for contract staff, by gender, at each stage of the process. Measure and identify anomalies in distribution across statuses and responsibilities. Continue to send existing statistics to Selection committee’s chairs. | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (+/-) 17. Variations in the chronological order of CVs (Code) (+/-) 27. Gender balance | 2025 and every year
| Responsible Unit | Indicator(s) / Target(s)
| Equality and non discrimination mission | Transmission of a guide and presentation to Selection committee’s chairmen.
Action 26 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : EQUALITY AND NON-DISCRIMINATION 26. Strengthen the action plan for professional equality and non-discrimination: assessment, design of the new plan and its follow-up. 26.1 Assess the job requirements of the Equality and Non-Discrimination Mission and make them permanent if necessary. Assess the employment needs of certain departments in relation to these issues. 26.2 AFNOR certification. | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (+/-) 17. Variations in the chronological order of CVs (Code) (+/-) 27. Gender balance | 26. 2025 and every year thereafter. 26.1 June 2025 26.2 January 2026
| Responsible Unit | Indicator(s) / Target(s)
| Department for managing the payroll and pensions Director General of services and presidency | 26. Drawing up tables. Transmission of tables. 26.1 Presentation of the plan to the authorities. 26.2 Submission of application
Action 27 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : EQUALITY AND NON-DISCRIMINATION Organisation of round tables and debates on the charters. 27.1 Increase interaction between research and action on equality and non-discrimination. To this end, create a list of researchers from the institution and associated institutions producing research related to the Equality and Non-discrimination Mission (see how to integrate this database into Plug in Labs). | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (+/-) 17. Variations in the chronological order of CVs (Code) (+/-) 27. Gender balance | 27. January 2025 27.1 June 2025 Update every two years
| Responsible Unit | Indicator(s) / Target(s)
| Equality and non discrimination mission | 27 Creation of at least one working group 27.1 Creation of the directory. Number of conferences or research seminars listed.
Action 28 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : SITUATIONS OF DISABILITY | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (-/+) 23. Research environment (-/+) 24. Working conditions | September 2025
| Responsible Unit | Indicator(s) / Target(s)
| HR disability officer | Development of the booklet and number of distributions.
Action 29 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : SITUATIONS OF DISABILITY Initiate the overhaul of the disability master plan. As part of this process, highlight the specific status of academic staff. | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (-/+) 23. Research environment (-/+) 24. Working conditions | June 2025 and June 2026
| Responsible Unit | Indicator(s) / Target(s)
| HR disability officer | Agenda meetings (june 2025) and publication of the new master plan
Action 30 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : SITUATIONS OF DISABILITY Develop a digital training offer on disability (video capsules). | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (-/+) 23. Research environment (-/+) 24. Working conditions | June 2025 and June 2026
| Responsible Unit | Indicator(s) / Target(s)
| HR disability officer | June 2025 : number of capsules posted on line June 2026 : number of views
Action 31 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : SITUATIONS OF DISABILITY To coordinate the activities of the UPN disability advisor with those of the faculties and departments. Provide a training base. | (+/-) 13. Recruitment (Code) (+/-) 14. Selection (Code) (-/+) 23. Research environment (-/+) 24. Working conditions | September 2026
| Responsible Unit | Indicator(s) / Target(s)
| HR disability officer | Minutes of meetings training project
Action 32 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : GENDER-BASED AND SEXUAL VIOLENCE Training by external partners for people in positions of responsibility. Development of in-house training on SEXUAL AND SEXIST VIOLENCE. Internalisation of gender-based and sexual violence training courses. Department-wide strategy. Training for new staff. Training for staff in positions of responsibility. | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (-/+) 34. Complains/ appeals | September 2025
| Responsible Unit | Indicator(s) / Target(s)
| Equality and non discrimination mission | Number of people trained per department. Rate of people trained per department. Rate of people trained and in responsibility in particular.
Action 33 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : GENDER-BASED AND SEXUAL VIOLENCE mproving support and knowledge of rights and services (developing institutional and community partnerships, producing guides). | (+/-) 4. Professional attitude (+/-) 10. Non discrimination (-/+) 34. Complains/ appeals | September 2025 and june 2026
| Responsible Unit | Indicator(s) / Target(s)
| Equality and Non-Discrimination Mission | 2025 : Creation of awareness-raising tools. Creation of an information guide on gender-based and sexual violence. 2026 : Developing partnerships with institutions and associations
Action 34 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
EQUALITY, NON-DISCRIMINATION AND GENDER-BASED AND SEXUAL VIOLENCE : REPORTING AND COORDINATION Raise awareness of the alert mechanisms, emphasising the guarantees of confidentiality. Promote the visibility of the whistleblowing unit through regular presentations, particularly in the training and research units (UFR), departments, doctoral schools and Research units. | (+/-) 10. Non discrimination (-/+) 34. Complains/ appeals | 2025 and every 2 years
| Responsible Unit | Indicator(s) / Target(s)
| Equality and non discrimination mission | Number of communications to UFR's directors and other levels.
Action 35 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
DEONTOLOGY AND PROTECTION OF WHISTLEBLOWERS To raise awareness of the prevention and remedial functions of the deontolgy referee and whistleblowers referee. 35.1 Publish a page describing these two functions on the Intranet site, with the referral e-mails, independently of the reference appearing on the current Ethics page: a text has been given to the team in charge of redesigning the site. 35.2 Systematise participation in the annual seminar for deontology referee of Higher Education organised by the Higher Education College of Deontology. Last held on 17 June 2024. 35.3 If requested, the deontology referee may attend meetings of elected councils. | (+/-) 1. Research freedom (+/-) 2. Ethical principles (+/-) 3. Professional responsibility (+/-) 4. Professional attitude (+/-) 7. Good practice in research (-/+) 34. Complains/ appeals | 35. 2025 and every year 35.1 September 2025 35.2 2025 and every year 35.3 September 2025
| Responsible Unit | Indicator(s) / Target(s)
| Presidency, communication direction and ethic committee | 35. Annual report including the quantity and quality of referrals. 35.1 Publication of pages 35.2 Attendance at the seminar 35.3 Number of interventions
Action 36 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - SUPPORT FOR RESEARCH AND DEVELOPMENT Reorganisation of the research departments to improve the research support provided to the research units. | (+/-) 5. Contractual and legal obligations (+/-) 6. Accountability (+/-) 8. Dissemination, exploitation of results (+/-) 11. Evaluation/ appraisal systems (-/+) 23. Research environment (+/-) 31. Intellectual Property Rights | September 2025
| Responsible Unit | Indicator(s) / Target(s)
| Research and doctoral studies department | Creation of a new service
Action 37 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - SUPPORT FOR RESEARCH AND DEVELOPMENT Improving access to information for research, in particular to encourage interdisciplinary research. 37.1 Update Plug in Lab regularly. 37.2 To develop channels and links with partners in order to strengthen the distribution of “Sciences for and with the society” activities externally and attract external audiences. 37.3 Define an online distribution policy for scientific events. | (+/-) 5. Contractual and legal obligations (+/-) 6. Accountability (+/-) 8. Dissemination, exploitation of results (+/-) 11. Evaluation/ appraisal systems (-/+) 23. Research environment (+/-) 31. Intellectual Property Rights | 37. June 2026 37.1 January 2027 37.2 et 37.3 January 2027
| Responsible Unit | Indicator(s) / Target(s)
| Research and doctoral studies department | 37. Number of interdisciplinary research projects. 37.1 Plug in Lab update. Access to the application. Number of connections. 37.2 and 37.3 Number of partnerships.
Action 38 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - SUPPORT FOR RESEARCH AND DEVELOPMENT Provide technical support to ensure the smooth running of the audiovisual recording equipment. 38.1 Distribute the procedure for recording scientific events. 38.2 Develop the university’s presence on Canal-U. | (+/-) 5. Contractual and legal obligations (+/-) 6. Accountability (+/-) 8. Dissemination, exploitation of results (+/-) 11. Evaluation/ appraisal systems (-/+) 23. Research environment (+/-) 31. Intellectual Property Rights | June 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Agenda meetings
Action 39 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - SUPPORT FOR RESEARCH AND DEVELOPMENT Review the university's system and introduce a dynamic display system (screens) to promote scientific events and campus life in general. | (+/-) 5. Contractual and legal obligations (+/-) 6. Accountability (+/-) 8. Dissemination, exploitation of results (+/-) 11. Evaluation/ appraisal systems (-/+) 23. Research environment (+/-) 31. Intellectual Property Rights | June 2025 June 2026 September 2027
| Responsible Unit | Indicator(s) / Target(s)
| Communication direction | 2025 : number of communications and quantified diagnosis 2026 : number of incentive communications Rate of increase in the number of videos online. 2027 : Deployment of a new signage system
Action 40 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - DISTRIBUTION OF INFORMATION Strengthen the network of communication officers within the Research unit. 40.1 / Development of the "actu Recherche" website and improving the visibility of the Research Newsletter | (+/-) 8. Dissemination, exploitation of results (-/+) 23. Research environment | 40. January 2026 40.1 June 2026
| Responsible Unit | Indicator(s) / Target(s)
| Communication direction | 40. Number of meetings organised and attendance rate. 40.1 The site goes online. Number of views of the Research Newsletter.
Action 41 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH - DISTRIBUTION OF INFORMATION Modernise the resources (guides, tutorials, videos, etc.) available to academic staff and improve their accessibility, distribution and updating. 41.1 Centralising and clarifying all the training on offer in the Research and doctoral studies department catalogue. Improve and complete the doctoral training catalogue. 41.2 Include research and teaching training in the HRD training plan. | (+/-) 8. Dissemination, exploitation of results (-/+) 23. Research environment | 41 and 41.1 June 2026 and october 2025 41.2 : 2025 and every year
| Responsible Unit | Indicator(s) / Target(s)
| Research and doctoral studies department and career support developpment | 41 and 41.1 Number of resources. Catalogue update. Annual training report. 41.2 : Publication of the catalogue. Annual training report.
Action 42 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : INTERNATIONALISATION AND MOBILITY Develop funding, incentives and recognition for international mobility. 42.1 Improve incentives and facilities for international mobility. Consider better integration into the doctoral programme. 42.2 Clarify information on international mobility. Organise information sessions (particularly within departments and laboratories). 42.3 Communicate the EDUC recommendations of the programme for young researchers. 42.4 Develop a section dedicated to international mobility (incoming and outgoing) in the Faculty Welcome Guide. 42.5 Opening up EDUC training courses to post-doctoral students. 42.6 Integrate mobility into teaching services, particularly in the context of double degrees. 42.7 Introduce a specific allowance for travel, particularly for double degrees. 42.8 Include the international dimension in job descriptions. 42.9 Consider collaboration between the International Relations Department and the Teaching staff department. | (-/+) 18. Recognition of mobility experience (Code) (-/+) 21. Postdoctoral appointments (Code) (-/+) 28. Career development (+/-) 29. Value of mobility (-/+) 30. Access to career advice | S2 2024/2025 for actions aimed at doctoral students/post-doctoral students S2 2025/2026 for actions aimed at ressearchers.
| Responsible Unit | Indicator(s) / Target(s)
| International and mobility department | Number of information meetings, number of international exchanges.
Action 43 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : WELCOMING FACULTY Assisting academic staff to find their way around the various departments that can help them with their administrative formalities. | (-/+) 28. Career development (-/+) 38. Continuing Professional Development | September 2026
| Responsible Unit | Indicator(s) / Target(s)
| Career Support Department, Social Action Department, Personnel department, International Relations Direction, International Relations and Mobility Department, Teaching staff department, Research and doctoral studies department | Reinforcement of information tools (guide, intranet, meetings, etc.) and number of communications. Measure visitor numbers.
Action 44 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : WELCOMING FACULTY Special arrangements for international faculty | (-/+) 28. Career development (-/+) 38. Continuing Professional Development | September 2026
| Responsible Unit | Indicator(s) / Target(s)
| Career Support Department, Social Action Department, Personnel department, International Relations Direction, International Relations and Mobility Department, Teaching staff department, Research and doctoral studies department | Reinforcement of information tools (guide, intranet, meetings, etc.) and number of communications. Measure visitor numbers.
Action 45 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : ACADEMIC FREEDOM, RESEARCH ETHICS, SCIENTIFIC INTEGRITY To initiate an institution-wide debate on the protection of academic staff in the exercise of their academic freedom. Involve the issues of scientific integrity and responsibility in public debate. | (+/-) 1. Research freedom (+/-) 2. Ethical principles (+/-) 3. Professional responsibility (+/-) 4. Professional attitude (+/-) 7. Good practice in research | January 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Meetings between the following bodies and referents: Research Ethics Committee, Scientific Integrity Officer, DPO, Whistleblower Officer, Ethics Officer.
Action 46 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : ACADEMIC FREEDOM, RESEARCH ETHICS, SCIENTIFIC INTEGRITY Offer support, in conjunction with the DPO, for personal protection committees. | (+/-) 1. Research freedom (+/-) 2. Ethical principles (+/-) 3. Professional responsibility (+/-) 4. Professional attitude (+/-) 7. Good practice in research | January 2026
| Responsible Unit | Indicator(s) / Target(s)
| LEGAL & INSTITUTIONAL AFFAIRS DEPARTMENT | Minutes of meetings
Action 47 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : TRAINING Disseminating information and opening up training courses, particularly on scientific integrity, to all academic staff. | (-/+) 38. Continuing Professional Development (-/+) 39. Access to research training and continuous development | september 2027
| Responsible Unit | Indicator(s) / Target(s)
| RESEARCH AND DOCTORAL STUDIES DEPARTMENT | Minutes of meetings Number of courses
Action 48 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH : CHARTES Undertake a review of the coherence of the charters and continue to implement them. | (-/+) 23. Research environment (-/+) 24. Working conditions | January 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Agenda meetings
Action 49 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : TAKING PART IN PUBLIC DEBATE AND DISSEMINATING RESEARCH IN A NATIONAL AND EUROPEAN CONTEXT Define and disseminate the uses of the university's signature as part of a new "institutional presentation brochure". Develop tools to support media representation | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | June 2026
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Publication of the corporate brochure and recommendations guide.
Action 50 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : TAKING PART IN PUBLIC DEBATE AND DISSEMINATING RESEARCH IN A NATIONAL AND EUROPEAN CONTEXT Creation of a list of academic staff willing to respond to requests for information on their research subjects. Creation of a monitoring table for press contributors. Inform and consult staff. | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | September 2025 and september 2026
| Responsible Unit | Indicator(s) / Target(s)
| Communication direction | Staff consultation and creation of the list and tracking table
Action 51 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : TAKING PART IN PUBLIC DEBATE AND DISSEMINATING RESEARCH IN A NATIONAL AND EUROPEAN CONTEXT To provide information on functional protection and the procedures in place when a teacher-researcher or researcher is concerned in the performance of his or her duties. | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | 2026
| Responsible Unit | Indicator(s) / Target(s)
Legal & institutional affairs department
Action 52 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : ENCOURAGE THE DEVELOPMENT OF COLLABORATIVE AND PARTICIPATORY RESEARCH Setting up a facility modelled on a Science Boutique. First phase: preliminary work and experimentation. Work process: questionnaire to teaching and research staff, interviews with partners and targeted staff to identify specific expectations in terms of participatory science. Recruitment of a partnership officer at the Research and doctoral studies department. 52.1 Set up a Boutique des sciences ticket office staffed by a project manager. Draw up a multi-year communication plan to publicise and promote the Science Boutique. 52.2 In the long term, consider developing the Science Boutique at European level. | (+/-) 9. Public engagement | 52. December 2026 52.1 and 52.2 January 2027
| Responsible Unit | Indicator(s) / Target(s)
| Research and doctoral studies department | 52. Creation of the Science Boutique. 52.1 and 52.2 Launch of the counter. Launch of communication plan. Number of new partnerships.
Action 53 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : ENCOURAGE THE DEVELOPMENT OF COLLABORATIVE AND PARTICIPATORY RESEARCH Facilitating partnerships between the school and cultural, social and economic players. 53.1 Improve feedback from the ALUMNI network 53.2 Draw up an inventory of existing and potential partnerships. In the short term, start at regional level. In the long term, extend to national, European and international levels. Disseminate the directory of partnerships. | (+/-) 9. Public engagement | January 2027
| Responsible Unit | Indicator(s) / Target(s)
| International Relations and Mobility Department Science Boutique Foundation | Information note
Action 54 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : ENCOURAGE THE DEVELOPMENT OF COLLABORATIVE AND PARTICIPATORY RESEARCH Include in the agreements the terms and conditions for compensating participants in participatory research (in particular transport, accommodation, meals). | (+/-) 9. Public engagement | June 2026 June 2027
| Responsible Unit | Indicator(s) / Target(s)
| Legal and institutional affairs department, Research and Doctoral studies department | Creation of the directory to be shared with the various departments Map the agreements to be amended. Drafting of a specific financial clause.
Action 55 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : STRUCTURING THE "SAPS" POLICY Articulate the university's 'SAPS' activities within its local ecosystem: bring together the research and Doctoral studies department, the common documentation department, the MSH-Mondes and La Contemporaine. | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | June 2025
| Responsible Unit | Indicator(s) / Target(s)
| Research and doctoral studies department | Number of meetings of the interdepartmental events coordination committe
Action 56 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : STRUCTURING THE "SAPS" POLICY Develop and disseminate cross-disciplinary initiatives aimed at all types of audience, including the general public, those who are not familiar with science and schoolchildren. | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | June 2026
| Responsible Unit | Indicator(s) / Target(s)
| Communication Direction, research and doctoral studies department | Number of actions proposed. Rate of change in the number of participants
Action 57 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : STRUCTURING THE "SAPS" POLICY Leading the network of communication officers within the Research Unit. Develop the network of "SAPS" referents within the Research Unit | (+/-) 8. Dissemination, exploitation of results (+/-) 9. Public engagement | 2026
| Responsible Unit | Indicator(s) / Target(s)
| Communication Direction, | Number of meetings and training courses. Number of meetings between the Committee and the "SAPS" referents.
Action 58 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
SUPPORT SCHEMES FOR RESEARCH PARTNERSHIPS AND "SCIENCE WITH AND FOR SOCIETY" ACTIVITIES : Support "SAPS" activities and train academic staff (training in mediation, communication or the scientific approach). Plan how training will be maintained once the "SAPS" label is no longer funded. | (-/+) 38. Continuing Professional Development (-/+) 39. Access to research training and continuous development | September 2025
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Number of calls for applications conducted with partners. Number of staff taking part in training courses.
Action 59 | GAP Principle(s) | Timing (at least by year’s quarter/semester)
MECHANISMS FOR SUPPORTING AND PROMOTING RESEARCH Elaborate a memo on the signature of scientific publications depending of each scientific area taking into account the Charter principle recommendations for citing authors and acknowledgements. | (-/+) 32. Co-authorship | September 2027
| Responsible Unit | Indicator(s) / Target(s)
| Presidency | Agenda minutes from the UR's directors council